# Project Planning Phase

| Date | 19-feb-2026 |
| --- | --- |
| Team ID | LTVIP2026TMIDS64562 |
| Project Name | Smart Sorting: Healthy vs Rotten Fruits & Vegetables Detection using Deep Learning |
| Maximum Marks | 4 Marks |

# Product Backlog & Sprint Schedule

## Sprint-1 — Dataset Preparation & Model Training

| Sprint | Functional Requirement (Epic) | User Story No | User Story / Task | Story Points | Priority | Team Members |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | Dataset Collection | USN-1 | As a developer, I collect fruit images dataset for training model | 3 | High |  |
| Sprint-1 | Dataset Collection | USN-2 | As a developer, I organize dataset into fresh and spoiled classes | 2 | High |  |
| Sprint-1 | Dataset Preparation | USN-3 | As a developer, I split dataset into train and test sets | 2 | High |  |
| Sprint-1 | Data Preprocessing | USN-4 | As a developer, I resize images to 224×224 for model input | 3 | High |  |
| Sprint-1 | Data Preprocessing | USN-5 | As a developer, I perform data augmentation using ImageDataGenerator | 5 | Medium |  |
| Sprint-1 | Model Development | USN-6 | As a developer, I design CNN model architecture | 5 | High |  |
| Sprint-1 | Model Training | USN-7 | As a developer, I train model using TensorFlow/Keras | 5 | High |  |
| Sprint-1 | Model Evaluation | USN-8 | As a developer, I evaluate model accuracy | 3 | Medium |  |

### Total Story Points — Sprint-1 = 28

## Sprint-2 — Prediction System & Web Application

| Sprint | Functional Requirement (Epic) | User Story No | User Story / Task | Story Points | Priority | Team Members |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-2 | Prediction System | USN-9 | As a developer, I load trained model for prediction | 2 | High |  |
| Sprint-2 | Prediction System | USN-10 | As a developer, I preprocess uploaded image | 3 | High |  |
| Sprint-2 | Prediction System | USN-11 | As a developer, I classify fruit type using CNN model | 5 | High |  |
| Sprint-2 | Prediction System | USN-12 | As a developer, I detect fresh or spoiled quality | 3 | High |  |
| Sprint-2 | Prediction System | USN-13 | As a developer, I display prediction confidence score | 2 | Medium |  |
| Sprint-2 | Web Application | USN-14 | As a user, I upload fruit image through web interface | 3 | High |  |
| Sprint-2 | Web Application | USN-15 | As a developer, I create Flask backend server | 5 | High |  |
| Sprint-2 | UI Development | USN-16 | As a developer, I design HTML/CSS user interface | 3 | Medium |  |
| Sprint-2 | Result Display | USN-17 | As a user, I view fruit type, quality and confidence result | 3 | High |  |
| Sprint-2 | Testing | USN-18 | As a developer, I test system and fix errors | 5 | High |  |

### Total Story Points — Sprint-2 = 34

# Project Tracker, Velocity & Sprint Details

| Sprint | Total Story Points | Duration | Sprint Start Date | Sprint End Date (Planned) | Story Points Completed | Sprint Release Date |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 28 | 7 Days | 01 Mar 2026 | 07 Mar 2026 | 28 | 07 Mar 2026 |
| Sprint-2 | 34 | 7 Days | 08 Mar 2026 | 14 Mar 2026 | 34 | 14 Mar 2026 |

# Velocity Calculation

Total Story Points = 28 + 34 = 62
Number of Sprints = 2

Velocity = 62 / 2 = 31 Story Points per Sprint